## General Session EDU
Copy to create activity checklist
| Activity | Time Frame | Description | Linked Templates and Examples
FALSE | Set parameters for externship | 3-6 months | Determine the size and scope of the externship experience to provide guidelines for recruiting. Consider: 1. Grade level of participanting educators 2. Number of paricipants (recommeded 25-40) 3. Dates (3 consecutive days)
FALSE | Set dates and times | 3-6 months | Virtual Externships are 15 hours = 8 am - 1 pm for 3 days; 3 virtual sessions each day; 8-10 employer sessions total; kick off and wrap up; 8 externship activities Establish recruitment strategy and registration deadlines for paricipants
FALSE | Prepare the educator and employer registration form | 10 weeks prior | Registration form gathers info on school, district, grades/subjects, contact info and any other information required for processing externship stipends
FALSE | Create educator and employer recruitment list | 10 weeks prior | List contacts for educator recruitment (i.e. principals, district leadership) and assign team members to reach out to contacts with relationships
FALSE | Update educator and employer flyer | 8-10 weeks prior | Update flyer to current externship dates, focus, contact info, and registration deadlines
FALSE | Send educator and employer recruitment emails | 8-10 weeks prior | Send recruitment email to contacts with fliers and any additional information such as registration deadlines, number of participants to recruit, etc.
FALSE | Update Participant Materials | 2-4 weeks prior | Create Externship Google Folder to be shared with participants. Update externship pre/post assessments and externship activities. Add updated form links to daily email templates and Activity Overview. | Externship Activities - NOT SHARED (TEMPLATE) Externship Resources - SHARED (TEMPLATE)
FALSE | Update Kick-off and Wrap up | 2-4 weeks prior | Update Kick-off and Wrap-up slide decks to reflect current externship programming and any focus or theme you want to highlight during the externship.
FALSE | Finalize Employer Session agenda | 1-2 weeks prior | Finalize Employer Session agenda with session titles, presenters, facilitator and join links.
FALSE | Create at-a-glance schedule | 1-2 weeks prior | Create an at-a-Glance schedule for participants and add to SHARED folder. This schedule is how educators know which session to attend and how to join.
FALSE | Close registration | 1 week prior | Close registration and double check all participant information is entered into participant list.
FALSE | Send Welcome Email to participants | 1 week prior | Send join link for the initial Kick-off session to participants as a calendar invite.
FALSE | Double check materials in educator resource folder | 1 week prior | Educator resource folder should include: 1. At-a-glance schedule 2. Participant list (names, schools, emails) 3. Activities handout 4. Folder for employer resources (slide decks and handouts)
FALSE | Send Welcome email | 1 week - 1 day prior | Send welcome email with link to Kick-off session, link to resource hub, and link to pre-externship survey (Activity 1).
EXTERNSHIP
FALSE | Facilitate Kick-off | First Day | Facilitate Kick-off meeting (orientation) for educator participants. Kick-off should include a way to frame the externship experience and its relation to educators classroom; logistics of the externship; and break out activities that allow educators to spend time getting to know members of their cohort.
FALSE | Facilitate Employer Sessions | Daily | Empoyer sessions are most effective when there is a Lead Facilitator and a Techical Facilitator. Technical facilitators are available to support educators and employers with difficulties, admit participants, manage the chat, and take responsibility for recording sessions. Lead Facilitators provide structure, consistency and guidance for the experience.
FALSE | Send Daily Activity Email | Daily | Daily emails are sent each morning of the externship. Emails should include links to the schedule, links to complete daily externship activities, and any other information participants may need. The daily emails provide a touch point for educators who have questions or need to communicate that they will be missing a session, etc.
FALSE | Update educator resource hub | Mid-point | As organizations share slide decks and handouts from their Employer Session, these resources can be added to the resource hub.
FALSE | Prepare PD certificates | Mid-point | PD Certificates are provided to participants who complete the externship. Once participants complete the requirements for the externship, PD certificates can be moved to the resource hub where participants can download them.
FALSE | Track activities completion | Daily | Monitor the completion of activities by participants. Some participants may need reminders to complete the activites and receive full PD hours for the externship.
FALSE | Facilitate Wrap up | Last Day | The Wrao-up session is an opportunity to reinforce the purpose of the externship, allow participants to share highlights of their experiences, celebrate the program, and let educators know next steps. The wrap-up should include a brief recap of the experience (such as participant feedback), breakout sessions for educators and attending employers to discuss and digest their learnings, and next steps required to complete the externship.
FALSE | Send Thank You email with links | 1 day post | Send a follow up email to participants to thank them for participating, provide links to the resource hub, and remind them to complete any outstanding activities or paperwork.
FALSE | Support final activity completion | 1-7 days post | Follow up with participants who have not completed activities so that they can complete the externship and receive full compensation and PD hours.
FALSE | Process stipends | 1-week post | Process stipends for all participants who completed externship requirements.
FALSE | Complete and upload PD certificates | 1-week post | Complete PD Certificates and upload to the resources folder for all participants who completed the externship.
FALSE | Update Resource folder | 1-week post | Add any final materials and resources from Employer Sessions to the resource hub.
FALSE | Compile recording links and upload | 1-3 weeks post | Collect Employer Session recording links and post them to the playlist.