## Campaign Video Support
Campaign Video Support
CFA will create 1-minute videos to help share about your project proposals at your schools! We will coordinate visiting your campus between March 23rd - 31st to capture footage for the campaign videos as well as footage for a celebration video at the end of the process.
Site | Check if you would like to receive campaign video support from CFA | Recording Day | Recording Time | Media Release Forms
Amy L. Houston | FALSE
Bernard Black | TRUE | 2023-03-30 | 1:30-2:30 | YES WE HAVE THEM
Cesar Chavez | TRUE | 2023-03-28 | 2:15 - 3:25 | Trying to verify
Ed and Verma Pastor | FALSE |  |  | Confirmed
Ignacio Conchos | FALSE
John R. Davis | FALSE
Martin Luther King Jr. | FALSE
Percy L. Julian | FALSE
Southwest | FALSE
T.G. Barr | FALSE
V.H. Lassen | FALSE

## Vote Days
RSD Vote Day Coordination 2023
It is almost time for Vote Days! The Campaign & Voting Phase is a fun and unique opportunity to involve students outside the steering committee, and sometimes families and staff, in deciding which project will be funded and implemented at your school. The district recommends that all schools hold their Vote Day between April 10th and April 14th and use an online platform such as Google Forms for the ballot to facilitate real-time election results. Schools will decide how to conduct the campus-wide vote during the Campaign Training on March 22nd. Some examples include: • Voting during a specific class period • Connecting the Vote Day to a campus event or assembly • Voting in a centralized location like a gym or library to mirror a real-life polling place
Site | Vote Day | Vote Time | Voting Location(s) | Polling Stations Needed (total number) | Vote Stickers Needed (1/student) | Materials Delivered | Volunteer Coverage / Visits | Link to Vote Day Action Plan
Example | 2023-04-12 | During lunch (11:30 am - 12:40 pm) | Cafeteria | 20 | 750 |  |  | Example School Vote Day Checklist & Plan
Bernard Black | 2023-04-10 | 8:30am-3:30pm | Cafeteria | 20 | 550 | TRUE | CFA (Madison, KaRa Lyn) RSD (Lynda)
Cesar Chavez | 2023-04-10 | 11:00am-12:45pm | Cafeteria | 2 Ballot Boxes | 415 | TRUE | CFA (KaRa Lyn) RSD (TBD)
Ed and Verma Pastor | 2023-04-14 | 8am-8:30am | Classrooms | N/A | 450 | TRUE
Ignacio Conchos | 2023-04-14 | 2:00-3:00 PM | Classrooms | N/A | 350 | TRUE
John R. Davis | 2023-04-04 | 11:30am - 12:30pm | Cafeteria | 10 | 200 | TRUE | 2 x CFA (KaRa Lyn, Madison) RSD (Mrs. Gestson, Lynda)
Martin Luther King Jr. | 2023-04-14 | During Lunch (10:40-11:50) | Cafeteria | 8 booths, 3 ballot boxes | 250 | TRUE | 3 x CFA (KaRa Lyn, Jackie, +1) RSD (Lynda)
Southwest | 2023-04-14 | During Lunch (9:45-12:20) | Cafeteria | 10 | 570 | TRUE | CFA (KaRa Lyn) RSD (Lynda + additional)
T.G. Barr | 2023-04-13 | 11:30am-1:00pm | Library | 20 | 354 | TRUE | Presentation 4/10: CFA (TBD), RSD (Lynda) Voting 4/13: CFA (KaRa Lyn, Jackie), RSD (Lynda)
V.H. Lassen | 2023-04-13 | Teacher Prep (12:00-2:30pm) | TBD | 10 | 300 | TRUE | 2 x CFA (Madison) RSD (Lynda)

## Evaluation
RSD Vote Day Coordination 2023
YOU DID IT!!! You've made it through voting and are on your way to the final phase of the SPB process! Next up, it is important to debrief how the process went and learn from students on the steering committee about SPB's impact on their experience. We will do this by conducting a process and impact evaluation. Guidance for this phase of the process will be given at the SPB Evaluation Overview sessions. Use this sheet to keep track of key steps needed to complete the evaluation. As always, please reach out if you have any questions or concerns.
Site | Parent Consent Forms Disseminated | Parent Consent Forms Collected | Evaluation Celebration Date KASP Administered + Process Evaluation (Suggested Week of May 1st) | [DEEP DIVE SCHOOLS ONLY] Focus Group Date + Time
Example |  |  | 2023-05-02
Bernard Black | FALSE | FALSE
Cesar Chavez | FALSE | FALSE
Ed and Verma Pastor | FALSE | FALSE
Ignacio Conchos | FALSE | FALSE
John R. Davis | FALSE | TRUE | 2023-05-03
Martin Luther King Jr. | TRUE | TRUE | 2023-05-03 | 5/15/2023 from 9-10 AM
Southwest | FALSE | FALSE
T.G. Barr | TRUE | FALSE
V.H. Lassen | TRUE | TRUE | 2023-05-03 | 5/5/2023 from 8-9 AM