| Timeline | Stage of PB | Resources (Links are not connected, but useful for an idea of types or resources) |
| --- | --- | --- |
| September 5th | LOL Conference | Kickoff Activity |
| September 18th | - SPB Orientation Virtual Meeting | SPB Informative Presentation LOL Meeting Schedule |
| October 2024 | PB Overview & Idea Collection |  |
| PB Overview & Idea Collection Training Video October 18 Training Video | Learn about their role in the PB process & Idea Collection Phase (Sponsor must watch and send training receipt by 10/18/24) | Idea Collection Video and Verification Idea Collection Survey Template (Optional) |
| PB Student Overview | School teams learn about the PB process & plan idea collection. | QCHS Presentation Rehearsal |
| Idea Collection by LOL Students | Collect ideas from students on campus “All In.” [DUE 11/04/24] | Please add a quick blurb on your idea collection process and include pictures Here. |
| November 2024 | Level 1 Approval & Proposal Development | PB Idea Collection |
| Proposal Development Training Video November 8 Training Video | Learn and share resources during the proposal development phase. (Sponsor must watch and send training receipt by 11/08/2024) | Proposal Development Training Video and Verification SPB Proposal Development Guide |
| 1-on-1 with Business & Operations November 12, 7-9 am November 13, 2-4 pm | Sponsors will attend a virtual meeting to share ideas collected and gather feedback/suggestions. Click here to book your time slot. | B & M Schedule Ideas Feedback Document (new) |
| Review, Sort, and Prioritize Ideas | LOL students review, sort & identify 4 Projects | OPTIONAL- Into Activity Proposal Guide ScorecardPB Research Guide Template |
| Research Top 4 & Collaborative sessions with the Principal | LOL, students complete the PB Research Guide in groups. They will identify their vision for the project. The principal meets with the LOL group to discuss possibilities and limitations. DUE 11/26/24 (Updated) | PB Research Guide Template |
| December 2024 | Proposal Development |  |
| Identify 4 Projects | Identify ideas for moving to the proposal development phase. PB final 4 [DUE 12/6/24] (Updated) | PB Final 4 |
| Vendor/ QCUSD Building & Construction Visits | If necessary, the District Office is responsible for coordinating vendor visits (The sponsor will be responsible for meeting the vendor) |  |
| Schedule Rehearsal Timeslot | Email Robin to schedule the January Rehearsal (Rehearsal week is January 20 and the week of Mar 24, 2025. | Rehearsal Sign-Up |
| Create a Proposal Slide Deck | Create a proposal Slide Deck for your site | SPB Presentation Template |
| January 2025 | Practice Proposal Presentation |  |
| Project Proposals | Proposal Projects Slide Deck [DUE 3/7/25] Share with Robin and Nicole | SPB Presentation Template |
| Practice Proposal Presentation | Presentation Rehearsal Week of January 20th and the week of Mar 24, 2025. Study Session Presentation Date 4/8/25 |  |
| Vote Day Selection | Coordinate your site vote day in February with the Principal [DUE 1/30/25] | Voting Day Information (What supplies you need?) Ballot Information (Information to put on voting ballots if voting by ballot) Vote Day Instructions |
| February 2025 | Campaign |  |
| Project Proposals | Proposal Projects Slide Deck [DUE 3/7/25] Share with Robin and Nicole | SPB Presentation Template |
| Campaign Training Video February 3 Training Video | (Sponsor must watch and send training receipt by 2/3) | Campaign Training Video |
| Campaign | Advocate for project proposals |  |
| Campus Vote February 21, 2025 | Campus Vote MUST be completed by February 21, 2025 |  |
| Winning Projects | Enter winning projects on 24-25 PB Projects Document (DUE 2/28/25) | 24-25 Winning Project |
| March 2025 | Presentation Rehearsals |  |
| Project Proposals | Proposal Projects Slide Deck [DUE 3/7/25] Share with Robin and Nicole | SPB Presentation Template |
| Practice Proposal Presentation | Presentation Rehearsal Week of January 20th and the week of Mar 24, 2025. Study Session Presentation Date 4/8/25 |  |
| April 2025 | Winning Proposal Video/Governing Board Presentation |  |
| Student Proposal Presentation to Governing Board April 8, 2025 | 4:30 pm Study Session presentation at District Office (LOL representatives and sponsor(s) must be present- 4 minutes maximum per site- 4-5 students max for the presentations. |  |
| Winning Proposal Video April 11, 2025 | LOL representatives will prepare the Winning Video | 24-25 Winning Video Folder |
| May- July 2025 | Implementation |  |
|  | Target Implementation Window May-July 20 |  |